## Slide 1
2S Module Production – Debriefing
ETP 2S Module Production Meeting – 27.03.2025 ●Stefan Maier

## Slide 3: 15 Modules in 16 Days
Long story short: Success!
  We took the lead! ; )

## Slide 4: Shift Scheduling
As already stated in the kick-off meeting the high granular scheduling of shifts and task is not feasible for a full scale production scenario
We will change from 8 time slots to 4 time slots
  2 in the morning 2 in the afternoon
  One “major” gluing task per 2 shifts
Try to keep HiWis busy
  Dicing test
  VI hybrids
  Skeleton assembly and test
  VI Bridges
  Assemble carriers
  Register parts on arrival → Logistics room ; )
We remove starting and end times as we will drop constraints in the pipeline

## Slide 5: Pipeline in general
Currently: 7 days
  Kapton gluing
  O.I. & Wire-bonding & encapsulation
  HV / IV test & Bare module assembly
  O.I. & Metrology & Hybrid gluing
  O.I. & Wire-bonding & quick test & encapsulation
  Encapsulation
  Full test
  7 days
In future: 13 days
  Kapton gluing
  O.I. & Wire-bonding & Encapsulation
  HV / IV test
  Bare module assembly
  O.I. Bare Modules
  Metrology
  Hybrid gluing
  O.I. Hybrid gluing
  Wire-bonding
  Quick test
  Encapsulation
  Encapsulation
  Full test

## Slide 6: Pipeline in general
Currently: 7 days
  Kapton gluing
  O.I. & Wire-bonding & encapsulation
  HV / IV test & Bare module assembly
  O.I. & Metrology & Hybrid gluing
  O.I. & Wire-bonding & quick test & encapsulation
  Encapsulation
  Full test
  7 days
In future: 13 days
  Kapton gluing
  O.I. & Wire-bonding & Encapsulation
  HV / IV test
  Bare module assembly
  O.I. Bare Modules
  Metrology
  Hybrid gluing
  O.I. Hybrid gluing
  Wire-bonding
  Quick test
  Encapsulation
  Encapsulation
  Full test
Time constraint in our pipeline

## Slide 7: Pipeline in general
In future: 13 days
  Kapton gluing
  O.I. & Wire-bonding & Encapsulation
  HV / IV test
  Bare module assembly
  O.I. Bare Modules
  Metrology
  Hybrid gluing
  O.I. Hybrid gluing
  Wire-bonding
  Quick test
  Encapsulation
  Encapsulation
  Full test
Constraint
  Limited by #of jigs
  Constrains us to do O.I. immediately followed by HV tail bonding
  Kapton gluing in the afternoon not feasible as the glue will not harden enough
  Module bonding schedule must account for this:
    Start only one module in the morning
    Wire-bond tails
    Bond remaining modules

## Slide 8: Front-End
Basic functionalities given by the software
  Login problems solved
Improvements mandatory
  Better overview pages
  Display of part history (comments)
  Edit tasks already done
Please use the comment field!
  Unify way of giving comments?
Lets hope our HiWis are good with JavaScript!

## Slide 9: Skeleton Assembly and Test
Hybrid VI:
  Leander identified 3 FEHs with scratches on the antenna and GND bond pads
  We concluded that we identify such hybrids with a red sticker to make clear that wire-bonding might be problematic
    Could also be done via the front-end but given the severity this is more straight forward and indicative
Skeleton assembly is a time consuming step
  We will try to stick and let it be done by HiWis, but this might not fully work out
Skeleton test can be run while another one is assembled

## Slide 10: Al-CF Bridges
With new no-go pins all “newer” bridges passed hole QC test
Thickness gauges machined by brown questionable
  Results in 10% dropout rate, contacted conveners
  We were told to measure bridges manually to crosscheck their gauges…

## Slide 11: Kapton Gluing
Incident: Pickup tool stuck to sensor
  Repairable
  Increased IV curve. Not severe
  Amount of glue in the pattern was reduced by 10%
We try and stick to do the gluing in the morning shift
  Keep 24h of curing as we need to wire-bond this in the morning
Recheck of gluing in the afternoon
Sensor showed some scratches during/after bare module assembly
  Assumption: They come from the repair
Buy dedicated dropper/pipette to apply isopropanol
HPK
ETP

## Slide 12: Sensor handling / Sensor Dicing
Now: Sensor processes is started after dicing test

## Slide 13: HV Tail Bonding and Encapsulation
Bonding went flawless
  Pattern recognition even better with new tails
Ease front-end usage: We skip the location scan, implemented

## Slide 14: HV / IV Test
Sensor tablets are now tagged:
  One caveat: First person in the morning must change tags from curing to untested. Error Prone How does one know he /she is the first one? Ideas?
Current recipe for measurement: 20 mins if everything goes well
  Place sensor, attach HV tail
  Place ion blower for 3-5 minutes
  Place bias needle
  Wait for 5% RH
  Measure
Problem sensors do charge up / are charged up after the HV test
  We had >500V on the jig after the measurement!
  Check relay setting and investigate
  Possible damage on sensors? (See later damaged channels)

## Slide 15: Microscopes on Gluing Stations
Looking forward for their upgrade
Should be done before we re-start
Experience with batteries?

## Slide 16: Bare Module Assembly / Metrology
Space sufficient for 2 jigs/table?
Different jigs yield slightly different alignment results
  Eager to see trends
  Recheck alignment pins
Jig #3 base plate uneven?

## Slide 17
Modul 12
Jig 1

## Slide 18
Modul 15
Jig 1

## Slide 19
Modul 20
Jig 1

## Slide 20
Modul 13
Jig 2

## Slide 21
Modul 1
Jig 2

## Slide 22
Modul 21
Jig 2

## Slide 23
Modul 16
Jig 3

## Slide 24
Modul 19
Jig 3

## Slide 25
Modul 17
Jig 4

## Slide 26
Modul 18
Jig 4

## Slide 27: Hybrid Assembly
Sufficient space for 2 jigs/table?
Further comments?

## Slide 28: Wire-bonding
In general even smoother than in October
4 modules and 20 pull test wire-bonds: 4 hours and 30 minutes
Where is the bottleneck?
  → PARTS
All pull test values between 6 and 13 g
Add dedicated microscope to make these pull tests and to inspect modules (?)

## Slide 29: Channel outliers
Scratched area
Most likely scratch
“Leaky strip effect”
?
?
?

## Slide 30: Encapsulation
Clash of MT / MPO connector (Zip tie) with module adapter
  Already modified, might need to reprint plastic piece
5cc and 30cc usage exercised
  Both run smooth
  Might need to adapt the 30cc program slightly
    Did not 100% hit the wire-bond feet on last modules, to be investigated
    Change dispensing height
6 modules tested with WBE height tool. All passed (<1mm above bottom sensor)
  9 more (incl 30cc modules) to do…

## Slide 31: Module Test
New failure mode (1 Module in October and one this time)
Single channel increases global leakage current significantly
Until we do not understand the cause and the impact on operation we must identify these channels and pull the corresponding channel
  We will start testing how this is triggered and its impact

## Slide 32: Module Test (2) - Noise

## Slide 33: Module Test (3) - IV

## Slide 34: Organization
Vacation / sickness leave etc: How to run the assembly line?
Need to come up with some knowledge transfer
  At the moment a lot of things happen “in the background” using custom scripts and manual work

## Slide 35: Outlook
Soon, we will get more FEHs
  They will have blocked alignment holes. Assembly without pins
New HV Tails are currently prepared at CERN.
  Update expected tomorrow in the electronics meeting
  IF they are good we can expect them mid of April
We expect ~120 or more carriers “soon”
  Assembly time should not to be underestimated
New type of SEH will be build “soon”, we do not expect that we need to build too much incomplete modules anymore
Soon: New modules must be finalized with another SEH
  Hybrid gluing
  Light shield attachment (encapsulant)
  Single module full test
  Burn in
Once we ramp again we will again start only doing one module per day, increasing towards 4 modules per day, depending on how much material we get. We will try to enter in a continuous production.

## Slide 37: Vacation